## Slide 1
FPGA PROFESSIONAL ASSOCIATION · AI-AUGMENTED SYSTEMS ENGINEERING
WEEK 10 OF 15
Integrated Risk Management
Risk identification, analysis, and handling across the lifecycle; risk registers; AI-specific technical risks; programmatic risk.
FPGA Professional Association · AI-Augmented Systems Engineering · Week 10
1

## Slide 2
WEEK 10 · SESSION PLAN
Today's Agenda & Objectives
Session agenda
1
The Risk Process
2
AI-Specific Technical Risks
3
Programmatic Risk
4
Risk-Informed Decisions
5
Studio activity & discussion
6
Deliverables & next week
By the end of this session, you can
Build and maintain a risk register with likelihood/consequence scoring and handling strategies.
Identify technical risks specific to AI components: hallucination, distribution shift, opacity, evaluation gaps.
Assess programmatic risks — supplier, obsolescence, schedule, cost — and their coupling to technical choices.
Integrate risk into decisions continuously rather than as a one-time exercise.
FPGA Professional Association · AI-Augmented Systems Engineering · Week 10
2

## Slide 3
WEEK 10 · CONCEPT 1 OF 4
The Risk Process
1.1
Identify → analyze → handle → monitor, on a cadence — risk is a process property of the program, not a document.
1.2
Likelihood × consequence gives the ranking; the 5×5 matrix is coarse but forces the conversation.
1.3
Handling options: avoid, mitigate, transfer, accept — each with an owner, a trigger, and a review date.
FPGA Professional Association · AI-Augmented Systems Engineering · Week 10
3

## Slide 4
WEEK 10 · CONCEPT 2 OF 4
AI-Specific Technical Risks
Generation risk: plausible-but-wrong outputs enter designs and documents wearing confident prose.
2.2
Drift risk: the world changes out from under the training data; performance decays without an error message.
2.3
Evaluation risk: benchmarks that miss the deployment distribution certify the wrong thing convincingly.
FPGA Professional Association · AI-Augmented Systems Engineering · Week 10
4

## Slide 5
WEEK 10 · CONCEPT 3 OF 4
Programmatic Risk
3.1
Single-source suppliers, long-lead items, and part obsolescence are multi-year bets hiding inside a parts list.
3.2
Schedule risk concentrates on the critical path — Week 7's longest-path lens is your early-warning instrument.
3.3
Cost risk compounds: technical rework, schedule slip, and scope growth feed one another.
FPGA Professional Association · AI-Augmented Systems Engineering · Week 10
5

## Slide 6
WEEK 10 · CONCEPT 4 OF 4
Risk-Informed Decisions
Every gate review is a risk review: what changed, what retired, what emerged, what the register says about proceeding.
4.2
Quantitative methods (Monte Carlo on schedule/cost, decision trees) sharpen the big bets beyond the color matrix.
4.3
The register's real product is arguments: a stated reason to accept each residual risk, owned by a named person.
FPGA Professional Association · AI-Augmented Systems Engineering · Week 10
6

## Slide 7
WEEK 10 · THE AI LENS
Where AI Enters This Week
As a Tool
Mining issue logs and past programs for leading indicators; Monte Carlo at scale; register hygiene automation.
As a Component
Each fielded model carries drift and evaluation risks that live on the register for the life of the product.
The Human Residual
Accepting residual risk — the signature that says this uncertainty, on this evidence, is worth carrying.
One question, every week: which mode is this — and what human role does it leave behind?
FPGA Professional Association · AI-Augmented Systems Engineering · Week 10
7

## Slide 8
WEEK 10 · APPLICATIONS
Across the Disciplines
Aerospace
Long-lead structural castings: one supplier slip re-plans the whole integration sequence.
Automotive
Component obsolescence: a discontinued part mid-program is a redesign wearing a memo.
Biomedical
Post-market model drift: patient populations shift, and last year's validation quietly ages.
Civil
Geotechnical uncertainty: the soil report is a sample, and the register should say so.
FPGA Professional Association · AI-Augmented Systems Engineering · Week 10
8

## Slide 9
WEEK 10 · STUDIO
In-Class Activity & Discussion
Studio activity
Register build: six risks for your project — two AI-specific, two programmatic, two technical — scored, with a handling strategy and trigger for each; present your top risk in ninety seconds.
Seminar discussion
Q1
Which risk on your project would survive every mitigation you can afford — and is it acceptable?
Q2
Who in your field is actually authorized to accept a residual risk, and how is it recorded?
FPGA Professional Association · AI-Augmented Systems Engineering · Week 10
9

## Slide 10
WEEK 10 · WRAP
Before Next Week
Read
INCOSE Hdbk (risk management); selected risk-management reference material; SEBoK risk articles.
Due
PS-3 due.
Next week
Week 11 — SE Management: Cost, Schedule & Technical Performance. Work breakdown structures and baselines; earned value management; technical performance measures, TRLs, and design reviews; AI in program analytics.
FPGA Professional Association · AI-Augmented Systems Engineering · Week 10
10