## Slide 1
FPGA PROFESSIONAL ASSOCIATION · AI-AUGMENTED SYSTEMS ENGINEERING
WEEK 11 OF 15
SE Management: Cost, Schedule & Technical Performance
Work breakdown structures and baselines; earned value management; technical performance measures, TRLs, and design reviews; AI in program analytics.
FPGA Professional Association · AI-Augmented Systems Engineering · Week 11
1

## Slide 2
WEEK 11 · SESSION PLAN
Today's Agenda & Objectives
Session agenda
1
WBS & Baselines
2
Earned Value in One Slide
3
Technical Performance & Maturity
4
AI in Program Analytics
5
Studio activity & discussion
6
Deliverables & next week
By the end of this session, you can
Construct a work breakdown structure and establish cost/schedule/technical baselines.
Compute and interpret earned-value measures (PV, EV, AC, SPI, CPI) and forecast at completion.
Define technical performance measures and use TRLs and design reviews to govern maturity.
Evaluate AI-based program analytics — schedule risk, cost estimation — and their limits.
FPGA Professional Association · AI-Augmented Systems Engineering · Week 11
2

## Slide 3
WEEK 11 · CONCEPT 1 OF 4
WBS & Baselines
1.1
The work breakdown structure decomposes the whole scope into elements someone can own, estimate, and finish.
1.2
Baselines freeze the reference: performance, cost, and schedule against which every variance is measured.
1.3
Change control is what keeps a baseline meaningful — a baseline that moves with the estimate measures nothing.
FPGA Professional Association · AI-Augmented Systems Engineering · Week 11
3

## Slide 4
WEEK 11 · CONCEPT 2 OF 4
Earned Value in One Slide
Planned Value: work scheduled. Earned Value: work done, priced at plan. Actual Cost: what it took.
2.2
SPI = EV/PV (schedule efficiency); CPI = EV/AC (cost efficiency); below 1.0 means the plan is losing.
2.3
Estimate at completion projects the ending from performance so far — an early, unsentimental forecast.
FPGA Professional Association · AI-Augmented Systems Engineering · Week 11
4

## Slide 5
WEEK 11 · CONCEPT 3 OF 4
Technical Performance & Maturity
3.1
TPMs track the product's key numbers (mass, power, throughput, accuracy) against planned profiles over time.
3.2
Technology readiness levels ladder maturity from principle (TRL 1) to proven-in-mission (TRL 9) — a shared honesty scale.
3.3
Design reviews (SRR, PDR, CDR, TRR) are the gates where evidence, not optimism, authorizes the next phase.
FPGA Professional Association · AI-Augmented Systems Engineering · Week 11
5

## Slide 6
WEEK 11 · CONCEPT 4 OF 4
AI in Program Analytics
Models trained on past programs forecast schedule slip and cost growth earlier than monthly variance reports.
4.2
Natural-language tools digest thousands of status entries into the anomalies a review board should see.
4.3
Limits stand: forecasts inherit past programs' biases, and no model attends the gate — accountability stays with the chair.
FPGA Professional Association · AI-Augmented Systems Engineering · Week 11
6

## Slide 7
WEEK 11 · THE AI LENS
Where AI Enters This Week
As a Tool
Slip prediction, cost-model calibration, review-package summarization — analytics that surface trouble early.
As a Component
If the product schedules or allocates resources at runtime (fleets, grids, lines), those optimizers are managed components.
The Human Residual
Setting baselines, chairing gates, and making the recover-replan-descope call when SPI and CPI go red.
One question, every week: which mode is this — and what human role does it leave behind?
FPGA Professional Association · AI-Augmented Systems Engineering · Week 11
7

## Slide 8
WEEK 11 · APPLICATIONS
Across the Disciplines
Aerospace
Satellite EVM: integration slips show in SPI months before the launch date admits it.
Civil
Megaproject recovery: CPI below 0.9 at 20% complete rarely heals itself — history is blunt.
Industrial
Production ramp: yield and takt-time TPMs tracked against profiles, gate by gate.
Software
Burn-down charts are EV in disguise — mapping them makes the two dialects one language.
FPGA Professional Association · AI-Augmented Systems Engineering · Week 11
8

## Slide 9
WEEK 11 · STUDIO
In-Class Activity & Discussion
Studio activity
EVM clinic: given a scenario (PV, EV, AC at month 6 of 18), compute SPI, CPI, and EAC; recommend recover, replan, or descope — and defend it to the “review board.”
Seminar discussion
Q1
What does your field use instead of earned value — and what question does it fail to ask?
Q2
Would you trust an AI slip forecast enough to move a review date? What evidence would it take?
FPGA Professional Association · AI-Augmented Systems Engineering · Week 11
9

## Slide 10
WEEK 11 · WRAP
Before Next Week
Read
Kossiakoff (SE management); INCOSE Hdbk (technical management processes); PMI PMBOK (selected).
Due
PS-4 released.
Next week
Week 12 — Certification, Assurance & Accountability. Why certification regimes exist; evidence and traceability demands across industries; assurance cases; accountable human sign-off.
FPGA Professional Association · AI-Augmented Systems Engineering · Week 11
10